## Project Plan
Project Name | Vue CMS
Project Manager | ToanCT.
Project Deliverable
Start Date | 2018-06-18
End Date | 2018-07-18
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status | 2018-06-18 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22 | 2018-06-23 | 2018-06-24 | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 | 2018-06-30 | 2018-07-01 | 2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05 | 2018-07-06 | 2018-07-07 | 2018-07-08 | 2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 | 2018-07-14 | 2018-07-15 | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | 2018-07-23 | 2018-07-24 | 2018-07-25
2016-03-16
Set kick-off meeting | ToanCT | 2018-06-18 | 2018-06-18 | 0 | Complete
Agree on objectives |  |  |  | 0 | Complete
Initiation
Detailed Reqs. |  |  |  | 0 | Complete
Hardward Reqs. |  |  |  | 0 | Overdue
Final Resource Plan |  |  |  | 0 | In progress
Staffing |  |  |  | 0 | In progress
Development
Techincal Reqs. |  |  |  | 0 | Not started
DB Development |  |  |  | 0 | Not started
API Development |  |  |  | 0 | Not started
UI Client |  |  |  | 0 | Not started
Testing |  |  |  | 0 | Not started
Dev. Complete |  |  |  | 0 | Not started
Operations
Hardware Config. |  |  |  | 0 | Not started
System Testing |  |  |  | 0 | Not started
Launch |  | 2018-07-18 | 2018-07-18

## Detail schedule
Tasks | Responsible | Start | End | Days | Status | 2018-06-18 | 2018-06-19 | 2018-06-20 | 2018-06-21 | 2018-06-22 | 2018-06-23 | 2018-06-24 | 2018-06-25 | 2018-06-26 | 2018-06-27 | 2018-06-28 | 2018-06-29 | 2018-06-30 | 2018-07-01 | 2018-07-02 | 2018-07-03 | 2018-07-04 | 2018-07-05 | 2018-07-06 | 2018-07-07 | 2018-07-08 | 2018-07-09 | 2018-07-10 | 2018-07-11 | 2018-07-12 | 2018-07-13 | 2018-07-14 | 2018-07-15 | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | 2018-07-23 | 2018-07-24 | 2018-07-25
Add config | ToanCT | 2018-06-18 | 2018-06-18 | 0 | In progress
Orders | AnhPD | 2018-06-18 | 2018-06-18 | 0 | In progress
News | HaiND | 2018-06-18 | 2018-06-18 | 0 | In progress
Create editor page itegrate TinyMCE | AnhPD |  |  | 0 | Not started
Upload images | ToanCT |  |  | 0 | Not started
Authenticate | ToanCT |  |  | 0 | Not started
ChartJS | ToanCT |  |  | 0 | Not started